# MT. KENYA NETWORK FORUM (MKNF)

# MEAL PLAN (2026 - 2032)

# Monitoring, Evaluation, Accountability & Learning Framework

# INTRODUCTION

This MEAL Plan accompanies the Mt. Kenya Network Forum (MKNF) Strategic Plan 2026 - 2032. It provides a clear, donor-aligned, results-driven framework to monitor progress, strengthen accountability, and ensure adaptive learning across all programs and pillars.

This MEAL system adheres to global standards, including:

- OECD-DAC Evaluation Criteria

- IFRC & UN MEAL Guidelines

- Participatory and community-led accountability tools

- Results-Based Management (RBM)

- Data protection and safeguarding principles

The MEAL Plan positions MKNF as a transparent, evidence-driven organization capable of delivering measurable, scalable, and community-owned climate justice outcomes.

PURPOSE OF THE MEAL SYSTEM

The MEAL system aims to:

- Track implementation of the Strategic Plan 2026 - 2032 across four pillars.

- Measure outcomes and long-term impact of MKNF’s interventions.

- Strengthen accountability to communities, donors, partners, and government.

- Document lessons, innovations, and best practices for replication and scaling.

- Improve decision-making through continuous learning and real-time data.

THEORY OF CHANGE (TOC)

The MEAL system is built on MKNF’s organizational Theory of Change:

- IF communities are empowered with knowledge, legal tools, and platforms…

- AND climate policies and governance systems become more transparent and inclusive…

- AND resilience initiatives are community-driven and sustainable…

- THEN communities will achieve climate justice, protect ecosystems, and secure dignified livelihoods.

The MEAL framework operationalizes this logic through indicators, targets, and evaluation pathways.

MEAL OBJECTIVES

- Measure impact of grassroots empowerment, legal advocacy, and climate resilience initiatives.

- Generate accurate, timely data for reporting and strategic decisions.

- Enhance transparency and accountability to all stakeholders.

- Promote learning, innovation, and adaptation across all program areas.

- Document models and evidence that position MKNF as a global climate justice leader.

RESULT AREAS & KEY INDICATORS (2026 - 2032)

## Impact Level Indicators

- Increased climate justice, environmental protection, and accountability in Mt. Kenya and ASAL counties.

- Improved household resilience for 5,000+ vulnerable households.

- Increased civic engagement and participation in climate governance (80% community satisfaction score).

- Strengthened ecosystems: 150,000 trees grown and monitored; improved water catchments.

## Outcome-Level Indicators (Aligned with Strategic Pillars)

### Pillar 1: Grassroots Empowerment & Civic Engagement

- of community members trained (target: 5,000; ≥60% women/youth)

- of functional community paralegal groups (target: 20)

- % increase in community participation in public decision-making

- Change in community knowledge (pre/post-test improvement ≥40%)

### Pillar 2: Legal Empowerment & Governance Accountability

- of legal cases filed/supported through litigation fund (target: 5 major wins)

- of climate policies influenced or adopted (target: 4 counties)

- Annual publication of County Climate Governance Scorecards

- % increase in compliance with public participation laws

### Pillar 3: Community Climate Resilience & Livelihoods

- of households benefiting from renewable energy solutions

- of youth/women-led green enterprises launched (target: 30)

- of trees grown (not just planted) and survival rate (%)

- of water catchments restored

### Pillar 4: Organizational Sustainability & Influence

- Annual revenue diversification rate

- of strategic partnerships established

- Annual publication of State of Climate Justice Report

- Digital reach and engagement metrics (podcasts, dashboards, knowledge products)

MEAL TOOLS & DATA COLLECTION METHODS

MKNF will deploy modern, participatory, and digital data systems, including:

### Quantitative Tools

- Digital data collection (ODK/KoBoToolbox)

- GIS mapping of trees, water sources & project sites

- Beneficiary registration & tracking system

- Renewable energy usage monitoring

### Qualitative Tools

- Focus Group Discussions (FGDs)

- Key Informant Interviews

- Community storytelling sessions

- Social accountability forums

- Case studies and testimonial videos

### Participatory Accountability Tools

- Community scorecards

- Public barazas & feedback forums

- SMS hotlines and helplines

DATA MANAGEMENT, QUALITY & SAFEGUARDING

MKNF will maintain strict data governance standards:

- Secure cloud-based storage

- Data anonymization for sensitive information

- Restricted access protocols

- Gender and age disaggregated reporting

- Safeguarding compliance for all MEAL activities

EVALUATION PLAN

MKNF will conduct:

- Baseline Study (Year 1) – establishes benchmarks

- Midline Evaluation (Year 3) – assesses performance, adjusts strategy

- Endline Evaluation (Year 7) – measures overall impact and sustainability

Where possible, mixed-method evaluations will be used.
External evaluators will be engaged for objectivity and independence.

LEARNING & ADAPTIVE MANAGEMENT

A structured learning system will include:

- Quarterly reflection and after-action reviews

- Annual Learning Reports

- Knowledge products (policy briefs, podcasts, infographics)

- Peer-learning exchanges across counties

- Documentation of best practices and innovations

MKNF will operate as a learning institution, not just implementing projects.

ACCOUNTABILITY TO COMMUNITIES & DONORS

### Community Accountability

- Regular community feedback forums

- Transparent budget sharing

- Public dashboards with progress indicators

- Complaint response mechanism (CRM)

### Donor Accountability

- Quarterly progress & financial reports

- Annual strategic reviews

- Audit reports and financial disclosures

- Transparent, data-driven communication

MEAL ROLES & RESPONSIBILITIES

- MEAL Manager: Leads MEAL system, analysis & reporting

- Data Officers: Field data collection & verification

- Project Officers: Pillar-specific monitoring

- Communications Officer: Visualization & dissemination

- Board MEAL Committee: Oversight & compliance

- Community Champions: Participatory monitoring

REPORTING SCHEDULE

| REPORT TYPE | FREQUENCY | AUDIENCE |
| --- | --- | --- |
| Monthly Activity Reports | Monthly | MKNF Leadership |
| Quarterly Progress Reports | Quarterly | Donors & Board |
| Financial Reports | Quarterly | Donors |
| Midline Evaluation | Year 3 | Donors & Partners |
| Endline Evaluation | Year 7 | All Stakeholders |
| State of Climate Justice Report | Annual | Public & Government |
| County Governance Scorecards | Annual | Public & CSOs |

# RISKS & MITIGATION MEASURES

- Political resistance:  Strengthen coalition advocacy

- Data inconsistency:  Staff training, digital tools

- Climate shocks:  Flexible programming & adaptation funding

- Community fatigue:  Rotational engagement, incentives

CONCLUSION

This MEAL Plan provides Mt. Kenya Network Forum with a strong, credible, and transparent system to measure impact, drive learning, and strengthen accountability.

It demonstrates that MKNF is:

- Results-driven

- Community-centred

- Evidence-based

- Scalable and sustainable

- A leader in climate justice and governance accountability

The MEAL Plan ensures that every project contributes to long-term systemic change for communities across the Mt. Kenya and ASAL region.